1428 Maple Street Outstanding Materials Estimate Work
Skokie Illinois   Project 00-0000   30 September 2026
The materials estimate remains preliminary and unpriced. Of 145 material lines, 64 have a supported base quantity and 81 still need a quantity. Even the counted items need specification, supplier or design review before purchase. This document identifies the remaining work, the relevant drawing references and the evidence needed to close each issue.
	Estimate status
	Current position

	Quantities
	64 quantified lines and 81 unresolved lines

	Prices
	No verified retailer prices or supplier quotations

	Review findings
	17 open items identified as C01 through C17

	Purchasing status
	Full purchasing list not ready for release



Work to complete first
1. Confirm the current approved plan set and the project scope. The supplied drawings are a 2022 permit issue for alteration and additions, with a detached garage.
2. Obtain written designer responses to conflicting footing, drainage, plumbing, wall and insulation requirements.
3. Complete the main-house dimension-based takeoff and the trade-specific pipe, wire and duct measurements.
4. Obtain fabrication schedules and shop information for engineered trusses, structural steel, windows and custom assemblies.
5. Convert quantities into verified stock lengths and supplier packages, then add compatible retailer prices and supplier quotes.
Scope that needs confirmation
C01: The revised SOW initially supports new detached single-family construction. This project is an alteration with second-story, rear and side additions. Treat the detached garage as a separate conditional scope. Rear exterior flatwork is outside the default pre-drywall milestone and must be separated from shared porch reinforcement and aggregate quantities. Existing basement slab, foundation portions, sump, water meter and 200 A panel are not presumed new purchases.
Recommended coordinators below describe who would normally resolve each issue. They are not assigned individuals or confirmed commitments.


Foundation and plumbing decisions
Resolve these design choices before using affected quantities to place orders. A drawing conflict should be closed by a documented response, not an estimating assumption.
Footings
C02 Finding Foundation plan calls for 24 in footing width; section shows 22 in.
Close with Architect/structural engineer to resolve width before concrete/rebar order.
Source: A3.0/1 p9; A4.0/5 p11. Recommended coordinator: architect and structural engineer.
Drainage and sump
C03 Finding Plans/riser connect to existing sump; section references new sump.
Close with Confirm retained versus new sump and discharge layout.
Source: A3.0/1 p9; A4.0/4 p11; P1.2 p18. Recommended coordinator: architect and plumbing contractor.
Water material
C04 Finding Supply diagram says all Type M copper; schedule and general notes specify Type L suspended water and Type K underground.
Close with Designer/plumber to resolve material by service; do not substitute PEX.
Source: P1.0 p17. Recommended coordinator: plumbing designer and contractor.
Water heater
C05 Finding Supply riser shows two new 50-gallon heaters; mechanical schedule lists 75-gallon Rheem.
Close with Resolve number, capacity and retained/new scope.
Source: P1.0 p17; M2.0 p16. Recommended coordinator: mechanical and plumbing designers.
Fixture scope
C06 Finding Schedule lists 3 new WC, 5 lavs, 2 tubs; diagrams label 5 WC, 7 lavs, 4 tubs new.
Close with Reconcile replacement versus retained fixtures before purchasing rough units.
Source: P1.0 p17; P1.2 p18. Recommended coordinator: architect and plumbing contractor.


Framing envelope and electrical decisions
Wall Type B
C07 Finding Type B text specifies 2x4 framing, while cavity dimension is 5-1/2 in.
Close with Resolve wall framing size and affected bearing walls.
Source: A1.2 p6. Recommended coordinator: architect and structural engineer.
Basement insulation
C08 Finding Type C lists 1-1/2 in faced mineral fiber; foundation sections list 1-1/2 in rigid insulation.
Close with Resolve basement assembly, R-value and coverage.
Source: A1.2/Type C p6; A4.0/4-5 p11; A4.1/4 p12. Recommended coordinator: architect and energy consultant.
Garage side door
C09 Finding Door 014 is outdoors on garage but scheduled Type A single-leaf interior.
Close with Confirm exterior-rated assembly/finish.
Source: A1.0 schedule p4; A1.3 p7. Recommended coordinator: architect and door supplier.
Garage grade beam
C10 Finding Reinforced grade beam is called out without section dimensions or reinforcing schedule.
Close with Obtain dimensioned grade-beam/rebar detail.
Source: A1.3/2 p7. Recommended coordinator: structural engineer.
Existing panel
C11 Finding Existing 200 A panel is identified; general notes also call for 200 A service as required. No circuit schedule supplied.
Close with Confirm capacity, retained service and required panel/breaker changes.
Source: A1.0 p4; E1.0 p13. Recommended coordinator: electrical designer and contractor.
Window safety and egress
C12 Finding W2 is 3x4 ft double-hung; egress well detail requires 5.7 SF clear opening. Supplier operation/clear opening is unverified.
Close with Obtain certified clear-opening and safety-glazing specifications.
Source: A1.1 schedule p5; A4.0/6 p11. Recommended coordinator: architect and window supplier.


Quantity work remaining by stage
C13 and C14: The drawings contain substantial information that has not yet been fully measured in the current estimate. An unresolved quantity does not always mean the drawing is missing. Some lines need additional takeoff work; others need a designer decision, routing information or a supplier schedule. Appendix A lists all 81 affected material IDs.
	Stage
	Open lines
	Required takeoff or confirmation

	Foundation & slab
	14
	Measure new slab and foundation polygons separately from retained work. Resolve footing width, elevations, drainage and reinforcing laps.

	Floor framing
	5
	Produce truss/member counts and spans. Obtain delegated truss design, steel cut lengths, rim/blocking and connection schedules.

	Wall framing
	11
	Measure new wall runs by type and height. Count opening/corner framing, headers, plates, lintels, blocking and stair framing.

	Roof framing
	6
	Count rafters and joists by roof zone. Measure ridges/valleys, ledgers, posts, blocking and connector requirements.

	Sheathing
	3
	Measure subfloor minus voids, wall surfaces and roof planes. Confirm panel grade, thickness, size and edge specification.

	Roofing / dry-in
	7
	Measure shingle and metal roof planes separately; measure eaves, valleys, ridges, ice barrier and flashing lengths.

	Exterior envelope
	4
	Measure WRB coverage and opening/penetration flashing. Confirm a garage-specific wall and WRB assembly.

	Windows & exterior doors
	0
	Counts are available. Resolve egress, safety glazing, door 014 and custom storefront/shop specifications before order.

	Rough plumbing
	9
	Measure diameter-specific copper/DWV/gas runs and fittings. Reconcile fixtures, heaters, sump and pre-close rough units.

	Rough electrical
	8
	Prepare box/circuit takeoff, conduit and conductor routes, garage feed, protection, panel changes and grounding.

	Rough HVAC
	6
	Measure duct centerlines by size, fittings and insulation; establish line-set, condensate and exhaust/combustion-air routes.

	Insulation
	5
	Measure net assembly areas; resolve basement material and R-values; confirm optional sound insulation and roof supports.

	Air sealing / fireblocking
	3
	Count penetrations and required backing/fireblocking locations; select compatible approved materials.



The open-line counts total 81 and include the garage annex. Zero open quantity lines for windows and doors does not mean those products are ready to purchase.


Pricing order conversion and release
Current drawings and inspection sequence
C15: Confirm the latest approved permit drawings and any addenda. The supplied set is marked Issue for Permit on 27 June 2022. A3.0 carries 28 June 2022 and M2.0 includes a 4 September 2019 title date. Obtain the applicable rough-trade, insulation and close-in inspection sequence. The estimate has not established approval status or current city requirements.
Compatible pricing
C16: Retail pricing must match the actual material specification and sold unit. Obtain verified Home Depot and Lowe's product mappings, project ZIP/store, package coverage, unit price, URL and capture date. Obtain separate supplier quotations for ready-mix, engineered members/trusses, fabricated steel, custom openings and scheduled HVAC equipment. No quotation request has been sent.
Purchasable quantities
C17: Confirm concrete design strength; the drawing note reads Fc=400pcs and is not reliable enough to set a mix specification. Confirm stock lengths, cut requirements, reinforcing laps, pipe sticks, wire spools, insulation packages and supplier minimums. Apply waste once, then round to verified order units. The garage roof conversion to 22 panels assumes 32 SF per panel and remains provisional.
Evidence required before purchasing
1. Current plan issue and retained-versus-new scope confirmed, with garage and exterior flatwork separated.
2. Conflicting design requirements resolved in writing, and the affected material lines updated.
3. Remaining geometry, member counts and trade route takeoffs completed or explicitly excluded from a defined purchasing package.
4. Supplier/shop information available for engineered and custom items; substitutions approved where necessary.
5. Base quantities, waste, stock/package conversion and final order quantities checked against the current documents.
6. Verified compatible prices and supplier quotes recorded with dates, units and scope. Unpriced items remain visible.
7. Estimator and responsible trade/design reviewers complete the review of the proposed purchasing package.
A fully priced retail basket would still exclude unpriced supplier items, labor, taxes, delivery, equipment rental, contractor markup and other project costs. BV360 does not determine whether construction passes inspection.


Appendix A Unresolved material lines
The following 81 IDs correspond to blank base quantities in 1428_Maple_Street_Materials_Estimate.xlsx. The workbook retains each line's full specification, calculation basis, source sheets and review note. Counted lines needing specification or order review are covered by the decisions above and remain visible in that workbook.
	Material ID
	Outstanding quantity

	
	House Foundation & slab

	M001
	New basement slab concrete

	M002
	New continuous footing concrete

	M003
	New foundation wall concrete

	M008
	Porch/rear thickened-edge concrete

	M012
	Foundation wall/footing rebar

	M015
	Sill anchor bolts

	M016
	PT sole plates and sill seal

	M017
	Foundation waterproofing

	M018
	Foundation exterior insulation

	M019
	Interior drain tile

	M020
	Drainage stone, sleeves and supports

	M021
	Rebar chairs/supports

	M022
	Underslab vapor barrier

	
	House Floor framing

	M025
	Engineered floor trusses

	M026
	Double floor trusses

	M027
	LVL headers

	M028
	Floor steel beams

	M029
	Rim boards, truss blocking and hangers

	
	House Wall framing

	M032
	Exterior studs

	M033
	Exterior plates

	M034
	Interior partition studs

	M035
	Interior partition plates

	M036
	Type B wall framing

	M037
	Basement furring framing

	M038
	Headers, king/jack studs and cripples

	M039
	Lintels and masonry support angles

	M040
	Blocking, straps, ties and framing fasteners

	M041
	Stair rough framing

	
	House Roof framing

	M042
	Main roof rafters

	M043
	Ceiling joists

	M044
	Ridges, valleys and doubled rafters

	M045
	Porch ledgers and connections

	M046
	Roof posts, blocking, ties and nails

	
	House Sheathing

	M047
	Floor subfloor

	M048
	Wall sheathing

	M049
	House/porch roof sheathing

	
	House Roofing / dry-in

	M050
	Main roof shingles

	M051
	Porch standing seam roof

	M052
	Roof underlayment

	M053
	Ice and water membrane

	M054
	Drip edge, flashing, boots and sealants

	M055
	Ridge vents and ridge cap

	
	House Exterior envelope

	M056
	Weather-resistive barrier

	M057
	Window/door flashing

	M058
	Envelope penetration seals

	
	House Rough plumbing

	M076
	Copper domestic branches

	M077
	New underground water service

	M078
	Water fittings, valves and supports

	M079
	Hot-water pipe insulation

	M080
	Cast iron DWV and fittings

	M081
	Gas rough piping

	M082
	Tub/shower rough units

	M086
	Water heaters and pre-close connections

	M087
	Sump system changes

	
	House Rough electrical

	M088
	Electrical conduit

	M089
	Branch-circuit conductors

	M090
	Feeder/garage circuit materials

	M091
	Outlet, switch and lighting rough boxes

	M092
	Panel/breaker modifications

	M093
	Grounding, bonding, connectors and supports

	M094
	Low-voltage cable and raceways

	
	House Rough HVAC

	M113
	Rigid round duct

	M114
	Rectangular duct and transitions

	M115
	Duct fittings, dampers, hangers and sealant

	M116
	Duct insulation

	M117
	Refrigerant piping and condensate

	M118
	Exhaust, dryer vent and combustion air

	
	House Insulation

	M119
	Exterior wall insulation

	M120
	Roof insulation

	M121
	Basement interior insulation

	M122
	Optional sound insulation

	M123
	Baffles and insulation supports

	
	House Air sealing / fireblocking

	M124
	Air-sealing materials

	M125
	Fireblocking/draftstopping

	M126
	Backing and pre-close framing

	
	Garage Foundation & slab

	M129
	Garage grade beam and reinforcement

	
	Garage Wall framing

	M130
	Garage wall studs and plates

	
	Garage Roof framing

	M137
	Outriggers, bridging and connections

	
	Garage Roofing / dry-in

	M140
	Garage underlayment/flashing/ice barrier

	
	Garage Exterior envelope

	M141
	Garage wall sheathing and WRB

	
	Garage Rough electrical

	M145
	Garage rough electrical package



References: revised SOW_PREFLIGHT_MATERIALS_ESTIMATOR.pdf, dated 29 September 2026; 18-sheet 1428 Maple Street permit set, project 00-0000; materials estimate dated 30 September 2026. PDF page references in this document refer to the supplied drawings.
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